## KANBAN
Kanban Task Tracking
Gruuper
Sam Richard, Brady Amunsdon, CJ Plantemoli
| Queue | Development |  |  | Done
| [1] Update NavBar UI Due: 2024/04/24 [1] Add more to classrooms page Due: 2024/04/24 [1] Fix Mobile view Due: 2024/04/24 [1] Unmatched Mems to Firebase? Due: 2024/04/24 [1] Randomizer animation Due: 2024/04/24 [1] SmartMatch animation Upgrade Due: 2024/04/24 [1] Bug when deleting student and refreshing Due: 2024/04/24 [1] ^and removing from unmatched members Due: 2024/04/24 [1] Report for smartmatch results Due: 2024/04/24 [1] Class groupchat Due: 2024/04/24 [1] Student submitted classmate preferences Due: 2024/04/24 [1] Professor to access student info Due: 2024/04/24 [1] Multiple assignments within a classroom, with the ability to show the current one and go back and see the old ones Due: 2024/04/24 [1] Admin account to see all groups, edit instructor, etc Due: 2024/04/24 [1] Log group changes Due: 2024/04/24 [1] Student/Faculty dashboard Due: 2024/04/24 [1] lmu registration requirement Due: 2024/04/24 [1] sync profile pic Due: 2024/04/24 [1] edit photo /reset password bug Due: 2024/04/24 | [1] Student Classroom View UI Update Due: 2024/04/24 |  |  | [3] Change Password Due: 2024/04/24 [1] Hide groups in Student View Due: 2024/04/24 [1] Make SmartMatch work Due: 2024/04/24 [1] Show profile details/Update UI Due: 2024/04/24 [1] Populate existing profile details Due: 2024/04/24 [1] Lock groups Due: 2024/04/24 [1] Unmatched Members List Due: 2024/04/24 [1] Update Home UI Due: 2024/04/24 [1] Wrong student view when joining a group Due: 2024/04/24 [1] If not instructor redirect to student view Due: 2024/04/24 [1] Fix New Group Area Due: 2024/04/24 [1] Group size + lock groups Due: 2024/04/24 [1] Firebase profile pic Due: 2024/04/24
|  | Proposed | In Progress | Done

## Queue
Kanban Template
Task | Status | Iteration | Create Date | Due Date | Assigned Date | Complete Date | Primary Contact | Demand | Project / Category
Remove From Classroom | Done |  | 2024-04-15 | 2024-04-24 |  |  |  | 2 | AGILE - KANBAN | [2] Remove From Classroom Due: 2024/04/24
Change Password | Done |  | 2024-04-15 | 2024-04-24 |  |  |  | 3 | AGILE - KANBAN | [3] Change Password Due: 2024/04/24
Hide groups in Student View | Done |  | 2024-04-15 | 2024-04-24 |  |  |  | 1 | AGILE - KANBAN | [1] Hide groups in Student View Due: 2024/04/24
Make SmartMatch work | Done |  | 2024-04-15 | 2024-04-24 |  |  |  | 1 | AGILE - KANBAN | [1] Make SmartMatch work Due: 2024/04/24
Show profile details/Update UI | Done |  | 2024-04-15 | 2024-04-24 |  |  |  | 1 | AGILE - KANBAN | [1] Show profile details/Update UI Due: 2024/04/24
Populate existing profile details | Done |  | 2024-04-15 | 2024-04-24 |  |  |  | 1 | AGILE - KANBAN | [1] Populate existing profile details Due: 2024/04/24
Lock groups | Done |  | 2024-04-15 | 2024-04-24 |  |  |  | 1 | AGILE - KANBAN | [1] Lock groups Due: 2024/04/24
Notify Students Button | Proposed |  | 2024-04-15 | 2024-04-24 |  |  |  | 2 | AGILE - KANBAN | [2] Notify Students Button Due: 2024/04/24
Unmatched Members List | Done |  | 2024-04-15 | 2024-04-24 |  |  |  | 1 | AGILE - KANBAN | [1] Unmatched Members List Due: 2024/04/24
Update NavBar UI | Proposed | [8 empty] | [1] Update NavBar UI Due: 2024/04/24
Update Home UI | Done | [8 empty] | [1] Update Home UI Due: 2024/04/24
Add more to classrooms page | Proposed | [8 empty] | [1] Add more to classrooms page Due: 2024/04/24
Wrong student view when joining a group | Done | [8 empty] | [1] Wrong student view when joining a group Due: 2024/04/24
Fix Mobile view | Proposed |  | 2024-04-22 | [6 empty] | [1] Fix Mobile view Due: 2024/04/24
If not instructor redirect to student view | Done |  | 2024-04-22 | [6 empty] | [1] If not instructor redirect to student view Due: 2024/04/24
Fix New Group Area | Done |  | 2024-04-22 | [6 empty] | [1] Fix New Group Area Due: 2024/04/24
Group size + lock groups | Done |  | 2024-04-23 | [6 empty] | [1] Group size + lock groups Due: 2024/04/24
Update Sign-Up UI | In Progress | [8 empty] | [1] Update Sign-Up UI Due: 2024/04/24
Student Classroom View UI Update | In Progress | [8 empty] | [1] Student Classroom View UI Update Due: 2024/04/24
Firebase profile pic | Done | [8 empty] | [1] Firebase profile pic Due: 2024/04/24
Unmatched Mems to Firebase? | Proposed | [8 empty] | [1] Unmatched Mems to Firebase? Due: 2024/04/24
Randomizer animation | Proposed | [8 empty] | [1] Randomizer animation Due: 2024/04/24
SmartMatch animation Upgrade | Proposed | [8 empty] | [1] SmartMatch animation Upgrade Due: 2024/04/24
Bug when deleting student and refreshing | Proposed | [8 empty] | [1] Bug when deleting student and refreshing Due: 2024/04/24
^and removing from unmatched members | Proposed | [8 empty] | [1] ^and removing from unmatched members Due: 2024/04/24
Report for smartmatch results | Proposed | [8 empty] | [1] Report for smartmatch results Due: 2024/04/24
Class groupchat | Proposed | [8 empty] | [1] Class groupchat Due: 2024/04/24
Student submitted classmate preferences | Proposed | [8 empty] | [1] Student submitted classmate preferences Due: 2024/04/24
Professor to access student info | Proposed | [8 empty] | [1] Professor to access student info Due: 2024/04/24
Multiple assignments within a classroom, with the ability to show the current one and go back and see the old ones | Proposed | [8 empty] | [1] Multiple assignments within a classroom, with the ability to show the current one and go back and see the old ones Due: 2024/04/24
Admin account to see all groups, edit instructor, etc | Proposed | [8 empty] | [1] Admin account to see all groups, edit instructor, etc Due: 2024/04/24
Log group changes | Proposed | [8 empty] | [1] Log group changes Due: 2024/04/24
Student/Faculty dashboard | Proposed | [8 empty] | [1] Student/Faculty dashboard Due: 2024/04/24
lmu registration requirement | Proposed | [8 empty] | [1] lmu registration requirement Due: 2024/04/24
sync profile pic | Proposed | [8 empty] | [1] sync profile pic Due: 2024/04/24
edit photo /reset password bug | Proposed | [8 empty] | [1] edit photo /reset password bug Due: 2024/04/24
Solo members | Proposed
Name change doesn't update | Proposed
profile details UI | Proposed
Looking for group feature

## Instructions
Using this template
* FIRST * Make a copy of this template. You may modify this for your use.
This template is designed to help you visualize the work to do, the work being done and the work completed. To effectively use this only work on the items proposed, finish the work planned until it is complete and moved to the work done.
Understand the processes and workflows
At the beginning of each iteration decide which work will need to be completed. Each of these tasks should be able to complete by themselves. On the Queue tab write each task that needs to be included in this iteration. You may category these pritoritize items, and include review, completion or other dates.
Publish and Share KANBAN tab

## HIDE-InProgress (hidden)
#REF!
In Progress |  | Proposed |  | Done
[1] Update Sign-Up UI Due: 2024/04/24 | In Progress | [2] Notify Students Button Due: 2024/04/24 | Proposed | [2] Remove From Classroom Due: 2024/04/24 | Done
[1] Student Classroom View UI Update Due: 2024/04/24 | In Progress | [1] Update NavBar UI Due: 2024/04/24 | Proposed | [3] Change Password Due: 2024/04/24 | Done
|  | [1] Add more to classrooms page Due: 2024/04/24 | Proposed | [1] Hide groups in Student View Due: 2024/04/24 | Done
|  | [1] Fix Mobile view Due: 2024/04/24 | Proposed | [1] Make SmartMatch work Due: 2024/04/24 | Done
|  | [1] Unmatched Mems to Firebase? Due: 2024/04/24 | Proposed | [1] Show profile details/Update UI Due: 2024/04/24 | Done
|  | [1] Randomizer animation Due: 2024/04/24 | Proposed | [1] Populate existing profile details Due: 2024/04/24 | Done
|  | [1] SmartMatch animation Upgrade Due: 2024/04/24 | Proposed | [1] Lock groups Due: 2024/04/24 | Done
|  | [1] Bug when deleting student and refreshing Due: 2024/04/24 | Proposed | [1] Unmatched Members List Due: 2024/04/24 | Done
|  | [1] ^and removing from unmatched members Due: 2024/04/24 | Proposed | [1] Update Home UI Due: 2024/04/24 | Done
|  | [1] Report for smartmatch results Due: 2024/04/24 | Proposed | [1] Wrong student view when joining a group Due: 2024/04/24 | Done
|  | [1] Class groupchat Due: 2024/04/24 | Proposed | [1] If not instructor redirect to student view Due: 2024/04/24 | Done
|  | [1] Student submitted classmate preferences Due: 2024/04/24 | Proposed | [1] Fix New Group Area Due: 2024/04/24 | Done
|  | [1] Professor to access student info Due: 2024/04/24 | Proposed | [1] Group size + lock groups Due: 2024/04/24 | Done
|  | [1] Multiple assignments within a classroom, with the ability to show the current one and go back and see the old ones Due: 2024/04/24 | Proposed | [1] Firebase profile pic Due: 2024/04/24 | Done
|  | [1] Admin account to see all groups, edit instructor, etc Due: 2024/04/24 | Proposed
|  | [1] Log group changes Due: 2024/04/24 | Proposed
|  | [1] Student/Faculty dashboard Due: 2024/04/24 | Proposed
|  | [1] lmu registration requirement Due: 2024/04/24 | Proposed
|  | [1] sync profile pic Due: 2024/04/24 | Proposed
|  | [1] edit photo /reset password bug Due: 2024/04/24 | Proposed
Proposed
Proposed
Proposed